## Slide 1: Dec. 2 Meeting Agenda
I. Brief introductions and summary of first meeting (10 minutes)
II. Progress report + articulation of next steps (10 minutes)
III. Formalizing participation of organizations (15 minutes)
IV. March 2 meeting with Washington Supreme Court (10 minutes)
V. Set next meeting, adjourn general meeting, and convene working groups (45 minutes)

## Slide 2: Working Group 2: Community Engagement
1. Engage in community outreach efforts to ensure that we are listening to interested/affected communities
2. Plan dialogue among the interested parties involved in the criminal justice system
3. Specifically, this will include public events that might be planned at each of the 3 law schools; consider other venues in order to foster greater community engagement

## Slide 3: Working Group 3: Research
Pull together the research and findings that exist that is specific to WA; where this doesn’t exist, pull together national stats (could include state specific if demographics and other social conditions justify comparison)
Time: complete by mid-December
Assess the research, including identifying strengths and weaknesses
Time: complete by mid-January
Develop abstracts and executive summaries (if they don’t already exist)
Time: complete by end of January

## Slide 4: Working Group 3 (cont.)
Identify areas where further work is necessary or beneficial; interface with working group 1 to assess feasibility of follow up research, and follow through
Time: uncertain
Make this work accessible to the public—the three law schools, web presence?
Time: complete by end of January
Develop in a publishable form the findings, and working with Group 4, the recommendations and implementation plan. Work to get all 3 law school’s law reviews to co-publish this material. In order to emphasize collective work that went into this, rather than individual authors, publish as the work product of Working Groups 3 and 4.
Time: submit spring 2011 cycle for fall 2011 publication? Too ambitious?

## Slide 5: Working Group 4
Develop recommendations that flow from Working Group 3’s work product
Time: though dependent on Group 3, begin work now based on findings and recommendations that already exist; complete by mid-February
Refine recommendations for structural reform targeted at institutional actors within system
Time: preliminary by mid-February; refined, late Spring 2011
Develop implementation plan
Time: Summer 2011
Interface with Working Group 1: Oversight to assess progress

## Slide 6: Working Group 5: Education
Develop educational programming for the following:
Bench
Bar
Law Enforcement
Public
Law schools
Colleges
High schools and below

## Slide 7: Working Group 1: Oversight
Make sure all of this gets done
Make sure all the working groups have the resources they need to complete their tasks
Develop metrics to assess progress or lack thereof
Communications strategy

## Slide 8
Race and the Criminal Justice System Task Force
WSBA
MBAs
Judicial
Commissions
Executive Commissions
AOC, including WSCCR and others?
Law Schools
ATJ Board
WAPA and Prosecuting Attorney Offices
WASPC and other Law Enforcement
Other Community Organizations
Legislative and other Local Government
TDA and Criminal Defense Bar
Other opportu-nities?